## Sheet1
Category | Label | Value1 | Value2 | Value3 | Value4 | Value5 | Value6 | Value7 | Value8 | Value9 | Value10
Bug ID | ID number | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
| Name | Undefined Language on Home Page. | ,,Galerija" button malefunction. | Register malefunction. | Register confirmation. | Log in confirmation | ,,O nama" (About us) section content | Dashboard page do not shows images. | Post link on images does not work. | Favourite button does not work | User account icon on post is malefunction
| Reporter | Vladimir Vranjes | Vladimir Vranjes | Vladimir Vranjes | Vladimir Vranjes | Vladimir Vranjes | Vladimir Vranjes | Vladimir Vranjes | Vladimir Vranjes | Vladimir Vranjes | Vladimir Vranjes
| Submit Date | 05.07.2019. | 05.07.2019. | 05.07.2019. | 05.07.2019. | 05.07.2019. | 05.07.2019. | 05.07.2019. | 05.07.2019. | 05.07.2019. | 05.07.2019.
Bug overview | Relates to | Home page | Home page | Home page | Home page | Home page | Home page | Home page | Home page | Home page | Home page
Screenshot | bar: Value1 1 to Value10 10
Environment | Platform | Java | Java | Java | Java | Java | Java | Java | Java | Java | Java
| Operating System | Windows 10 | Windows 10 | Windows 10 | Windows 10 | Windows 10 | Windows 11 | Windows 12 | Windows 13 | Windows 14 | Windows 15
| Browser | Google Chrome | Google Chrome | Google Chrome | Google Chrome | Google Chrome | Google Chrome | Google Chrome | Google Chrome | Google Chrome | Google Chrome
Bug details | Steps to reproduce | - Open browser; - Go to page: http//localhost/izlet/index.php. | - Open browser; - Go to page: http//localhost/izlet/index.php; - Scroll down on home page; - Try to click on ,,Galerija" button. | - Open browser; - Go to page: http//localhost/izlet/index.php; - Go to Register (Not a member?) area; - Register more then once with identical data; | - Open browser; - Go to page: http//localhost/izlet/index.php; - Go to Register (Not a member?) area; - Input data; - Click on Register button. | - Open browser; - Go to page: http//localhost/izlet/index.php; - Enter Log in data; - Click on Log in button; - Get back to Home page. | - Open browser; - Go to page: http//localhost/izlet/index.php. | - Open browser; - Go to page: http//localhost/izlet/index.php; - Register/Log in. | - Open browser; - Go to page: http//localhost/izlet/index.php; - Register/Log in. | - Open browser; - Go to page: http//localhost/izlet/index.php; - Register/Log in; - Click on favourite icon (star). | - Open browser; - Go to page: http//localhost/izlet/index.php; - Register/Log in.
| Expected result | One language on Home page. | Go to ,,Galerija" page. | Site should not allow registration with same data more then one time. | Confirmation that registration was sucesfull. | Confirmation on every page during session that user is loged in. | ,,O nama" (About us) section should show some info about company, or link to that info. | Images should be shown on Dashboard page. | Click on image should show post or image. | Colour of star should change on each click ( from color to without color...) | After clicking on ours user account button site should lead us to our account page
| Actual result | Three different languages on Home page. | Impossible to click on ,,Galerija" button. | It is possible to register more then once with same data. | There is no confirmation that that registration was sucesfull. | After clicking on Log in button user does not know on every page during session is he loged in. | ,,O nama" (About us) section does not show some info about company, or link to that info. | Images are not shown on Dashboard page. | Click on post image does not show anything. | After clicking on favourite (star) button nothing happens. | After clicking on user account button on post nothing happens.
| Description | There are three different languages on Home page (Serbian, English and Latin (Lorem Ipsum)) instead of one. | It's impossible to click on,,Galerija" button when you scroll down on Home page. | You can enter more then one time same data in each field in Registration area. Site allows different people to register with same data. | When potential user input data and click on Register button there is no confirmation that registration was sucessfull. | After clicking on Log in button user is sent to Dashboard page, but if he wants to move back to Home page he has no confirmation that he is still loged in. There is no any mark about that except on Dashboard page. | Instead of showing some information about company/site ,,O nama" (About us) section shows Lorem Ipsum text. | Posts on Dashbord page contain images which are not shown. | Click on image (which is not shown) does not lead anywhere - it does not show post or image. | Favourite button (star within post) should be functional. It should show color if we click on it, which means that this post is among favorites. Instead button does nothing. | After clicking on ours user account button site should lead us to our account page instead nothing happens.
Bug tracking | Severity | Medium | High | High | Medium | Medium | Medium | Medium | Medium | Medium | Medium
| Assigned to | Dusan | Dusan | Dusan | Dusan | Dusan | Dusan | Dusan | Dusan | Dusan | Dusan
| Priority | Medium | High | High | Medium | Medium | Medium | Medium | Medium | Medium | Medium
Notes | Notes | There should be selector for favourabe language. | Probably some bug with CSS. | - | - | - | - | - | - | - | -